## RACI for Emergency change
Activity | Change Manager | E-CA | CA | Implementation | Change Owner | Delivery Manager | Requester
Raise RfC for emergency change | I | I |  | R | AR | R | R
Validate need for emergency change | A R | R |  |  | R | R | R C I
Convene EC | AR | I |  | C |  | C | C
Approve a change | AR | R |  |  | R | R | R
Schedule, coordinate, build and implement change | A | C I |  | R | R | C I | I
Post Implementation Review | A R |  | R | R | R | C I | I
Legend:
[8 empty] | Responsible (R) - Those who do work to achieve the activity. | Accountable (A) - The resource ultimately accountable for the completion of the task. There must be exactly one A specified for each activity. | Consulted (C) - Those whose opinions are sought. Two-way communication. | Informed (I) - Those who are kept up-to-date on progress. One-way communication